{"text_format":"1","workbook":"xlsx","n_sheets":3,"sheets":["LISTA","FERIADOS","CRONOGRAMA"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"LISTA","index":0,"n_rows":13,"n_cols":8,"rows_kept":13,"cut":false,"hidden":false,"merged":[]}
["ORDEM","PROCESSO","ATIVIDADE","DURAÇÃO","INÍCIO","FIM","INÍCIO REAL","FIM REAL"]
[1,"Projeto-1","Definir o escopo do Projeto",2,"2024-07-01",{"$f":"WORKDAY(E2,D2,FERIADOS!$A$2:$A$15)","v":"2024-07-03"},"2024-07-01","2024-07-03"]
[2,"Projeto-1","Identificar as Atividades",1,"2024-07-03",{"$f":"WORKDAY(E3,D3,FERIADOS!$A$2:$A$15)","v":"2024-07-04"},"2024-07-03","2024-07-05"]
[3,"Projeto-1","Sequenciar as Atividades",1,"2024-07-04",{"$f":"WORKDAY(E4,D4,FERIADOS!$A$2:$A$15)","v":"2024-07-05"},"2024-07-05","2024-07-06"]
[4,"Projeto-1","Desenvolvimento e testes",5,"2024-07-05",{"$f":"WORKDAY(E5,D5,FERIADOS!$A$2:$A$15)","v":"2024-07-15"},"2024-07-06","2024-07-10"]
[5,"Projeto-1","Homoloação do projeto",1,"2024-07-15",{"$f":"WORKDAY(E6,D6,FERIADOS!$A$2:$A$15)","v":"2024-07-16"},"2024-07-10","2024-07-17"]
[6,"Projeto-1","Go Live",1,"2024-07-15",{"$f":"WORKDAY(E7,D7,FERIADOS!$A$2:$A$15)","v":"2024-07-16"}]
[7,"Projeto-2","Definir o escopo do Projeto",3,"2024-07-01",{"$f":"WORKDAY(E8,D8,FERIADOS!$A$2:$A$15)","v":"2024-07-04"},"2024-07-01","2024-07-04"]
[8,"Projeto-2","Identificar as Atividades",3,"2024-07-03",{"$f":"WORKDAY(E9,D9,FERIADOS!$A$2:$A$15)","v":"2024-07-08"}]
[9,"Projeto-2","Sequenciar as Atividades",1,"2024-07-04",{"$f":"WORKDAY(E10,D10,FERIADOS!$A$2:$A$15)","v":"2024-07-05"}]
[10,"Projeto-2","Desenvolvimento e testes",3,"2024-07-05",{"$f":"WORKDAY(E11,D11,FERIADOS!$A$2:$A$15)","v":"2024-07-11"}]
[11,"Projeto-2","Homoloação do projeto",1,"2024-07-11",{"$f":"WORKDAY(E12,D12,FERIADOS!$A$2:$A$15)","v":"2024-07-12"}]
[12,"Projeto-2","Go Live",1,"2024-07-12",{"$f":"WORKDAY(E13,D13,FERIADOS!$A$2:$A$15)","v":"2024-07-15"}]

{"sheet":"FERIADOS","index":1,"n_rows":15,"n_cols":2,"rows_kept":15,"cut":false,"hidden":true,"merged":[]}
["DATA","OBS"]
["2024-01-01","Confraternização Universal"]
["2024-02-12","Carnaval"]
["2024-02-13","Carnaval"]
["2024-03-29","Paixão de Cristo"]
["2024-04-21","Tiradentes"]
["2024-05-01","Dia do Trabalho"]
["2024-05-30","Corpus Christi"]
["2024-07-09"]
["2024-09-07","Independência do Brasil"]
["2024-10-12","Nossa Sr.a Aparecida - Padroeira do Brasil"]
["2024-11-02","Finados"]
["2024-11-15","Proclamação da República"]
["2024-11-20","Dia Nacional de Zumbi e da Consciência Negra"]
["2024-12-25","Natal"]

{"sheet":"CRONOGRAMA","index":2,"n_rows":22,"n_cols":21,"rows_kept":22,"cut":false,"hidden":false,"merged":[]}
["PROCESSO/ORDEM","ATIVIDADE","INICIO","FIM","PROGRESSO","2024-07-01","2024-07-02","2024-07-03","2024-07-04","2024-07-05","2024-07-06","2024-07-07","2024-07-08","2024-07-09","2024-07-10","2024-07-11","2024-07-12","2024-07-13","2024-07-14","2024-07-15","2024-07-16"]
["Projeto-1",null,"2024-07-01","2024-07-16",0.90909090909090906]
[1,"Definir o escopo do Projeto","2024-07-01","2024-07-03",1]
[2,"Identificar as Atividades","2024-07-03","2024-07-04",1]
[3,"Sequenciar as Atividades","2024-07-04","2024-07-05",1]
[4,"Desenvolvimento e testes","2024-07-05","2024-07-15",1]
[5,"Homoloação do projeto","2024-07-15","2024-07-16",1]
[6,"Go Live","2024-07-15","2024-07-16",0]
["Projeto-2",null,"2024-07-01","2024-07-15",0.25]
[7,"Definir o escopo do Projeto","2024-07-01","2024-07-04",1]
[8,"Identificar as Atividades","2024-07-03","2024-07-08",0]
[9,"Sequenciar as Atividades","2024-07-04","2024-07-05",0]
[10,"Desenvolvimento e testes","2024-07-05","2024-07-11",0]
[11,"Homoloação do projeto","2024-07-11","2024-07-12",0]
[12,"Go Live","2024-07-12","2024-07-15",0]
[]
[]
[null,"Legenda"]
["g","Fora do prazo e duração estipulada"]
["g","Fora do prazo, porém dentro da duração estipulada"]
["g","Entregue dentro do prazo"]
["g","Entregue antes do prazo"]